## Essence Card Progression
Team Members | Responsibility_1 | Responsibility_2 | Responsibility_3 | Responsibility_4 | Remarks
Jayant Soni | Data Acquisition | Government Dataset Research | Data Lake | Data Quality | Proposed allocation — confirm with team
Honey Singh | ETL Pipeline | PostgreSQL Warehouse | Data Transformation | Integration | Proposed allocation — confirm with team
Gautam | Airflow | Pipeline Orchestration | Automation | Testing Support | Proposed allocation — confirm with team
Sugam | SQL Analytics | Dashboard | Visualization | Documentation | Proposed allocation — confirm with team
Alphas | Manager | Card_No. | Start_Date | Completion_Date | Remarks
Opportunity | Jayant Soni | [1, 3, 4] , [5] |  |  | Identify road-safety problem and validate available government data ¦ Primary manager only; proposed allocation.
Stakeholder | Honey Singh | [1, 2] , [3, 4] , [5, 6] |  |  | Identify stakeholder needs and define the analytical requirements for dashboard and reporting. ¦ Primary manager only; proposed allocation.
Requirements | Honey Singh | [1, 2, 3, 4] , [5, 6] |  |  | Coordinate functional/non-functional requirements, define scope, priorities, risks, and module dependencies. ¦ Primary manager only; proposed allocation.
Software Systems | Gautam | [1 to 6] |  |  | Set up Python, PostgreSQL, MinIO, Airflow, Docker and Git ¦ Primary manager only; proposed allocation.
Work | Jayant Soni | [1, 5] , [2] , [3, 4] |  |  | Coordinate all four members and ensure module integration ¦ Primary manager only; proposed allocation.
Way of Working | Gautam | [1, 2, 3] , [4, 5, 6] |  |  | Weekly sprints, Git workflow, progress tracking and integration ¦ Primary manager only; proposed allocation.
Team | Honey Singh | [1, 3] , [2, 4] , [5] |  |  | Shared testing, documentation and viva preparation ¦ Primary manager only; proposed allocation.

## Requirements
Project Title | RoadInsight India – Historical Indian Road-Accident Data Engineering & Analytics Platform
Project Start Date | 23-08-2026
Project End Date | TBD
Lead | Honey Singh
Remarks | 4-member team; batch-oriented Data Engineering and Analytics project using government road-accident data. Dates/statuses below are planning values unless marked otherwise.
Functional Requirements (FR) — decomposed
ID | Requirement | Priority | Risk | Module | Acceptance / completion condition | Dependency | Remarks
FR-01.1 | Identify compatible MoRTH/OGD annual road-accident datasets | High | Low | Data Acquisition | Source/year and expected fields are recorded before ingestion | — | Use official government sources selected for the project.
FR-01.2 | Retrieve selected CSV/PDF resources using a repeatable Python process | High | Medium | Data Acquisition | Selected files can be retrieved again with the same configuration | FR-01.1 | PDF/CSV handling may differ by source.
FR-01.3 | Record source URL, year, filename and retrieval metadata | High | Low | Metadata / Traceability | Each raw input has source metadata | FR-01.2 | Supports auditability.
FR-01.4 | Store raw files without modifying the original content | High | Low | MinIO Raw Lake | Downloaded file is stored in source/year/file organisation | FR-01.2 | Raw layer is treated as immutable.
FR-02.1 | Validate input schema and expected columns | High | Medium | Data Quality | Missing/unexpected fields are reported | FR-01.4 | Schema changes should not silently pass.
FR-02.2 | Check nulls, duplicates, data types and value ranges | High | Medium | Data Quality | Validation report records failures by check | FR-02.1 | Use Pandas/pandera/custom checks as appropriate.
FR-02.3 | Standardise inconsistent state names and categorical values | High | Medium | Data Quality | Known variants map to one canonical value | FR-02.2 | Mapping should be documented.
FR-02.4 | Quarantine invalid records with reason codes | High | Medium | Data Quality | Failed rows are separated and the reason is retained | FR-02.2 | No silent dropping of invalid records.
FR-03.1 | Standardise column names and reshape source tables to a canonical form | High | Medium | ETL / Transformation | Curated output follows the defined schema | FR-02.3 | Handles differences between annual reports.
FR-03.2 | Load validated data into PostgreSQL fact and dimension tables | High | Medium | PostgreSQL Warehouse | Validated records load with PK/FK constraints | FR-03.1 | Target grain must remain consistent.
FR-03.3 | Prevent duplicate records at the defined fact-table grain | High | Medium | PostgreSQL Warehouse | Duplicate grain records are rejected/detected | FR-03.2 | Grain: state, year and applicable category.
FR-04.1 | Create Airflow DAG for data retrieval | Medium | Medium | Airflow Orchestration | DAG can run retrieval task on schedule/on demand | FR-01.2 | Annual/batch workflow.
FR-04.2 | Create Airflow validation and ETL tasks with dependencies | High | Medium | Airflow Orchestration | Tasks execute in the intended order | FR-02.1, FR-03.1 | Failed upstream tasks stop dependent tasks.
FR-04.3 | Configure retries and execution logging | Medium | Medium | Airflow Orchestration | Failure and retry information is visible in task logs | FR-04.2 | Avoid silent pipeline failures.
FR-05.1 | Create state/year trend analytics | High | Low | SQL Analytics | Queries return year-wise accident/fatality trends | FR-03.2 | Use only measures supported by source data.
FR-05.2 | Create rankings and category comparisons | High | Low | SQL Analytics | Ranking/category queries return reproducible results | FR-05.1 | Rates only where denominators are available.
FR-05.3 | Create dashboard filters, charts and tables | High | Medium | Dashboard | User can filter and view selected analytical outputs | FR-05.1 | Streamlit/Metabase is planned.
FR-06.1 | Link analytical outputs back to source/year metadata | Medium | Low | Metadata / Traceability | Output can be traced to source period/file | FR-01.3, FR-03.2 | Useful for validation and reporting.
Non-functional Requirements (NFR) — decomposed
ID | Requirement | Priority | Risk | Module | Acceptance / completion condition | Dependency | Remarks
NFR-01.1 | Pipeline is reproducible and rerunnable | High | Low | Airflow / Git | Same configuration can reproduce the batch workflow | FR-04 | No manual hidden steps in the main pipeline.
NFR-01.2 | Raw inputs and source metadata are preserved | High | Low | MinIO / Metadata | Original inputs remain available for reprocessing | FR-01 | Supports reproducibility.
NFR-02.1 | Pipeline failures are logged and do not silently drop data | High | Medium | Airflow / Data Quality | Failed tasks and rejected rows have visible reasons | FR-02, FR-04 | Quarantine invalid records.
NFR-03.1 | Warehouse maintains data integrity using keys and constraints | High | Medium | PostgreSQL | PK/FK and grain checks pass | FR-03 | Measures should be non-negative where applicable.
NFR-04.1 | Code is modular and maintainable | High | Low | Python / SQL / Git | Functions/modules have clear responsibility and documentation | All FRs | Keep configuration separate from logic.
NFR-05.1 | Data lineage is auditable | High | Low | Metadata / MinIO / PostgreSQL | Source, year and retrieval information is retained | FR-01.3, FR-06.1 | Use stable identifiers where practical.
NFR-06.1 | System performs adequately for the project's modest batch data volume | Medium | Medium | PostgreSQL / SQL | Expected analytical queries complete without unnecessary distributed processing | FR-05 | No streaming engine required for current scope.
NFR-07.1 | Access to raw/warehouse services is controlled | Medium | Low | MinIO / PostgreSQL / Docker | Credentials are externalised and not hard-coded | All FRs | No secrets committed to Git.
NFR-08.1 | Dashboard is understandable and usable | Medium | Low | Dashboard | Labels, filters and units are clear | FR-05.3 | Keep visualisations focused on project questions.
NFR-09.1 | Environment is portable across team machines | Medium | Low | Docker Compose | Core services can be started using documented setup | All modules | Document setup and configuration.
Coding Standards
Standard | Python: PEP 8 style, descriptive snake_case names, small reusable functions, docstrings for important functions.
Standard | SQL: clear table/column naming, consistent snake_case, explicit joins, readable CTEs for complex queries.
Standard | Configuration: keep paths, credentials and environment-specific settings outside source code; do not hard-code secrets.
Standard | Git: meaningful commits, branch/merge discipline, and project README/setup documentation.
Standard | Data code: retain source metadata, avoid silent row drops, and document transformations/mappings.

## Traceability Matrix
Requirement | Priority | Risk | Module | Sprint | Owner | Dependency | Remarks
FR-01 | High | Medium | Data Acquisition | 1 | Jayant Soni | Official source availability | Dataset inventory, retrieval and metadata
FR-02 | High | Medium | Data Quality | 3 | Jayant Soni | FR-01 | Schema, null, duplicate, type/range and mapping checks
FR-03 | High | Medium | ETL / PostgreSQL Warehouse | 4 | Honey Singh | FR-02 | Canonical transformation and warehouse loading
FR-04 | Medium | Medium | Airflow Orchestration | 6 | Gautam | FR-01, FR-02, FR-03 | Scheduling, retries, logging and reruns
FR-05 | High | Low | SQL Analytics / Dashboard | 7 | Sugam | FR-03 | Trends, rankings, category comparisons and dashboard
FR-06 | Medium | Low | Metadata / Traceability | 2 | Jayant Soni | FR-01 | Source/year/file lineage
NFR-01 | High | Low | Airflow / Git | 1 | Gautam | All modules | Reproducible batch execution
NFR-02 | High | Medium | Airflow / Data Quality | 3 | Gautam | FR-02, FR-04 | Visible failures and quarantine
NFR-03 | High | Medium | PostgreSQL Warehouse | 5 | Honey Singh | FR-03 | PK/FK and grain integrity
NFR-04 | High | Low | Python / SQL / Git | 1 | Honey Singh | All modules | Modular maintainable implementation
NFR-05 | High | Low | Metadata / MinIO | 2 | Jayant Soni | FR-01 | Auditability and lineage
NFR-06 | Medium | Medium | PostgreSQL / SQL Analytics | 5 | Sugam | FR-03 | Adequate performance for modest volume
NFR-07 | Medium | Low | MinIO / PostgreSQL / Docker | 2 | Gautam | FR-02 | Controlled service access
NFR-08 | Medium | Low | Dashboard | 7 | Sugam | FR-05 | Clear filters, labels and outputs
NFR-09 | Medium | Low | Docker Compose | 8 | Gautam | All modules | Portable setup
Dependency analysis between project modules
Module | Data Acquisition | MinIO Raw Lake | Data Quality | ETL | PostgreSQL | Airflow | Dashboard
Data Acquisition | — | Feeds raw files | Feeds validation | Feeds source schema | — | Triggered by DAG | —
MinIO Raw Lake | Receives files | — | Reads raw inputs | Reads validated/raw inputs | — | Storage task dependency | —
Data Quality | Uses source files | Reads raw | — | Pass/fail gate | — | Validation task | —
ETL | Uses metadata/schema | Reads raw | Requires valid data | — | Loads curated data | ETL task | —
PostgreSQL | — | — | — | Receives curated data | — | Load task | Feeds analytics
Airflow | Orchestrates | Orchestrates | Orchestrates | Orchestrates | Orchestrates | — | Can trigger refresh
Dashboard | — | — | — | — | Reads analytical tables | May follow successful run | —

## Budget & Purchase
Particulars | Cost per unit | Nos. | Year / Month | Year / Month | Year / Month | Remarks
Manpower | [5 empty] | Team members are existing student team; no external manpower cost entered.
Recurring | [5 empty] | Open-source/self-hosted stack planned; recurring cost TBD if cloud/hosting is used.
Non-recurring | [5 empty] | No purchase assumed at planning stage.
Contingency | [5 empty] | TBD; keep blank until actual project expenses are known.
Overhead | [5 empty] | TBD; institute/team overhead not provided.
Total | [5 empty] | Do not estimate until actual purchases/hosting are known.
Particulars | Vendor | Nos. | Purchase_Date | Cost | GST | Remarks
No purchases recorded yet | TBD |  | TBD |  |  | Record any actual hardware, hosting or other purchases here.

## Sprint Plans
Project Title | RoadInsight India – Historical Indian Road-Accident Data Engineering & Analytics Platform
Project Start Date | 23-08-2026
Project End Date | TBD
Lead | Honey Singh
Sprint_No. | Sprint_Start_Date | Sprint_End_Date | Tentative Deliverables | Module_Start | Module_End | Status | Responsible | Priority | Remarks
1 | 23-08-2026 | 29-08-2026 | Project scope, dataset inventory, source metadata plan | Data Acquisition | Metadata / Traceability | Planned | Jayant Soni | High | Confirm source fields, years and project assumptions.
2 | 30-08-2026 | 05-09-2026 | Python ingestion and MinIO raw layer | Data Acquisition | MinIO Raw Lake | Planned | Jayant Soni; Gautam | High | Raw files organised by source/year/filename; preserve originals.
3 | 06-09-2026 | 12-09-2026 | Data-quality validation and quarantine | Data Quality | Data Quality | Planned | Jayant Soni; Honey Singh | High | Schema, null, duplicate, type/range and state-name checks.
4 | 13-09-2026 | 19-09-2026 | Canonical ETL and curated dataset | ETL / Transformation | ETL / Transformation | Planned | Honey Singh | High | Document mappings and transformations.
5 | 20-09-2026 | 26-09-2026 | PostgreSQL star-schema warehouse | PostgreSQL Warehouse | PostgreSQL Warehouse | Planned | Honey Singh; Sugam Umale | High | fact_accident plus dimensions; enforce keys and grain.
6 | 27-09-2026 | 03-10-2026 | Airflow DAG, retries, logging and rerun workflow | Airflow Orchestration | Airflow Orchestration | Planned | Gautam | Medium | Connect retrieval → validation → ETL → load dependencies.
7 | 04-10-2026 | 10-10-2026 | SQL analytics and Streamlit/Metabase dashboard | SQL Analytics | Dashboard | Planned | Sugam Umale | High | Trends, rankings, category comparisons and filters.
8 | 11-10-2026 | 17-10-2026 | End-to-end integration, testing, documentation and demo | Testing | Testing / Documentation | Planned | Gautam; All members | High | Run from raw source to dashboard and record issues/fixes.
Note | Sprint dates are tentative planning dates derived from the recorded project start date; actual progress/completion should be updated by the team.

## Test Sheet
Module | Function | Start_Date | End_Date | Status | Test_Id / Ticket_Id | Date | Status | Team_Member | Remarks
Data Acquisition | Retrieve selected source file |  |  | Planned | T01 |  | Not Run | Jayant Soni | Check file can be retrieved and metadata is recorded.
MinIO Raw Lake | Store raw file unchanged |  |  | Planned | T02 |  | Not Run | Gautam | Compare file hash/size after storage where practical.
Data Quality | Schema validation catches missing column |  |  | Planned | T03 |  | Not Run | Jayant Soni | Use a controlled invalid input.
Data Quality | Null/duplicate/type/range checks |  |  | Planned | T04 |  | Not Run | Jayant Soni | Verify failures are reported.
Data Quality | Invalid rows are quarantined with reason code |  |  | Planned | T05 |  | Not Run | Honey Singh | No silent dropping.
ETL | State/category mapping and canonical transformation |  |  | Planned | T06 |  | Not Run | Honey Singh | Check expected output schema.
ETL / PostgreSQL | Row/grain reconciliation after load |  |  | Planned | T07 |  | Not Run | Honey Singh | Check no duplicate fact grain.
PostgreSQL | PK/FK and non-negative measure constraints |  |  | Planned | T08 |  | Not Run | Sugam Umale | Validate integrity constraints.
Airflow | Failed task retry and logging |  |  | Planned | T09 |  | Not Run | Gautam | Check failure is visible and retry occurs.
Airflow | End-to-end rerun from source to warehouse |  |  | Planned | T10 |  | Not Run | Gautam | Repeat without manual hidden steps.
SQL Analytics | Year-over-year state trend query |  |  | Planned | T11 |  | Not Run | Sugam Umale | Compare query result with source totals.
Dashboard | Filter and chart update |  |  | Planned | T12 |  | Not Run | Sugam Umale | Check filters, labels and units.
Traceability | Output can be linked to source/year |  |  | Planned | T13 |  | Not Run | Jayant Soni | Verify lineage metadata is available.